## Slide 1: Network Automation Integration
Discover & Design
Build
Testing
Deploy
Training
Project kickoff
Requirements via In-Person Workshop
Implementation Strategy
Detailed Design Flow Diagrams
Ansible Server Deployment
Playbooks
Build Test Environment
Super-User Test Cases
Shore up Gold Standard Config
Begin Production Building
Update Monitoring and CMDB
Train Network Engineering Staff
Provide Manuals and Runbooks
Activities & Work Products

## Slide 2: Network Automation Projects
Project Identification
Versioning Control
Ansible Server
Approved script
Network Equipment
Network Administrator
Testing Team
Network Engineering
Templates
Playbooks
Modules
Create
Provision
Push
Deploy

## Slide 3
Ansible Life Cycle

## Slide 5: Deployment Roadmap to Success
Kickoff
Week 1
Discover & Design
Weeks 2 - 8
Server Buildout
Weeks 9 & 10
Testing
Weeks 11 - 13
Deployment / End User Rollout
Week 14
Training
Week 15

## Slide 6: Week 1 – Kickoff Meeting
Meeting Agenda
Identifying Resources
Determine Automation Technologies
Define Security Concerns
Formulate Roadmap
Kickoff
Week 1
Discover & Design
Weeks 2 - 8
Framework Build
Weeks 9 & 10
Testing
Weeks 11 - 13
Deployment / End User Rollout
Week 14
Training
Week 15

## Slide 7: Weeks 2 - 8 – Discover & Design
Discovery
Technologies to be automated
Existing automation scripts
Current configuration timelines
Existing Build Inconsistencies
Kickoff
Week 1
Discover & Design
Weeks 2 - 8
Framework Build
Weeks 9 & 10
Testing
Weeks 11 - 13
Deployment / End User Rollout
Week 14
Training
Week 15
Design
Toolsets Standards
Scripting Standards
Server Environment / location
Data Flows

## Slide 8: Weeks 9 & 10 – Framework Build
Kickoff
Week 1
Discover & Design
Weeks 2 - 8
Framework Build
Weeks 9 - 10
Testing
Weeks 11 - 13
Deployment / End User Rollout
Week 14
Training
Week 15
Ansible
Define Deploy Version
Configure Inventory File
Configure .cfg File
GitLab
Develop Team Page
Define Authentication
Configure “.cfg” File
VSCode
Define Deploy Version
YAML/JSON standards
Bash integration

## Slide 9: Weeks 11 - 13 – Testing
Testing
Develop Testing Sandbox
Add Technologies
Develop Scripts
Super-User testing
Kickoff
Week 1
Discover & Design
Weeks 2 - 8
Framework Build
Weeks 9 & 10
Testing
Weeks 11 - 13
Deployment / End User Rollout
Week 5
Training
Week 6

## Slide 10: Week 14 – Deployment / End User Rollout
Kickoff
Week 1
Discover & Design
Weeks 2 - 8
Framework Build
Weeks 9 & 10
Testing
Weeks 11 - 13
Deployment / End User Rollout
Week 14
Training
Week 15
Deployment
Production Automation Scripts
Individually Manage Workloads
Monitor Production

## Slide 11: Week 15 – Training
Training
Finalize Documentation
Confirm user access
Training provided for Engineering Team
Kickoff
Week 1
Discover & Design
Weeks 2 - 8
Framework Build
Weeks 9 & 10
Testing
Weeks 11 - 13
Deployment / End User Rollout
Week 14
Training
Week 15